## Sheet1
S.no | Category (Metadata Type) | Bug Description | Issue faced in (Org Name) | Status | Prioritiy | Root Cause | Solution | Solution verified by | Next Action | Fix Owner | Reviewed by | Completed Date | Tested Date | Deployment Date
1 | Fields | System audit fields should not be considered |  | Delivered | High | Metadata API includes System fields | Removed System audit fields during extraction: "CreatedDate", "LastModifiedById", "LastModifiedDate", "CreatedById" | Aravind | Roll it back | Dhivya | Aravind | 2015-05-11 | 2015-05-12 | 2015-05-12
2 | Buttons | 2 System button are added extra when the count is compared with buttons visible in the UI |  | Open | High | Metadata API includes System Buttons |  |  | 13-may: Discuss with Avinash for Solution | Aravind
3 | Approval Process | Count of Approval process in object 360 and the power map is different | ASDData | Open | Medium |  |  |  |  | Aravind
4 | Workflow count | Count of Workflows does not match with the workflow count in the org | Cardinal Health | Open | Medium |  |  |  |  | Aravind
5 | Page layout | Number of page layouts in metadata api and stored in Salesforce is not the same | ALL | Not a Bug | Low | Work.com layouts metdata file doesn’t have object name in the front. Our logic extracts object information from file name and process it. Object name is realate to the layout record in page_layout__C | Some layouts are not getting inserted into salesforce because they don’t have the corresponding objects inserted which acts as a foreign key. The metadata api will not retrieve and insert the objects that belong to the managed package and so the layouts of those objects also will not be inserted. |  |  | Aravind
6 | Profile _ tab | Failures in tabs | ASDData | Closed | Medium | Some tabs don’t have object names, they will fail in the current tool | Have implemeted the describealltabs() functionality available from api v31.0 and above. | Aravind |  | Dhivya | Aravind | 2015-06-24 | 2015-06-24 | 2015-06-24
7 | Profile - Field Access | Failures in storing profile - field permissions | ASDData | Open | Low | Significant failures ocurrs in storing profile - field access into salesforce |  |  |  | Dhivya
8 | Profile - layout Access | Failures in Profile Layout permissions | ASDData | Open | Low | Significant failures ocurrs in storing profile - layout access into salesforce |  |  |  | Dhivya
9 | All metada | Analyze in each metadata and see where are all we can find the relation with Object | NA | Closed | High | Most of the metadata which can be related to object are already stored with relation to Sobject__c | Completed | Avinash |  | Muthu/Dhivya |  | 2015-06-12 | 2015-06-12 | 2015-06-12
10 | New | Profile - Object like powermap for security model | NA | Open | Medium |  |  |  |  | Aravind
11 | new | Bring powermap for asd objs and analyze the required objects | NA | Closed | Medium |  | Completed | Avinash |  | Aravind/Dhivya/Avinash |  | 2015-05-18 | 2015-05-18 | 2015-05-18
12 | Login | User unable to login when having hongkong hours | NA | Open | High | Formating the time stamp coverts the time to be time zone dependent | Use direct time stamp for comparison |  |  | Aravind
13 | All metada | To analyse the metadata which contains concatenated field values | NA | Closed | Medium |  | Completed |  |  | Muthu |  | 2015-07-14 | 2015-07-14 | 2015-07-14

## GE Specific
S.no | Category (Metadata Type) | Bug Description | Issue faced in (Org Name) | Status | Prioritiy | Root Cause | Solution | Solution verified by | Next Action | Fix Owner | Reviewed by | Completed Date | Tested Date | Deployment Date
1 | Code Metrics | Code Metrics - All Charts are missing | No Data Displayed in Code Metrics specific to Top Violation, Code Violation Per Priority, Coding Units and Lines of Code due to Failed in single class GE_PW_PGS_AddVerifi_Controller_Test.cls. Exclude this class then Novacop rerun. | Closed | Medium | Running the particular file on novasuite plugin gives the same error(ClassCastException) as well. On further investigation, the file has a unique line, where normally the pagereference is set to a VF Page URL in apex code. But Here it is rather a SOQL query. pgRef1 = new pageReference('/'+[Select Opportunity__c from GE_ES_Request_Type__c where id =:ReqType].Opportunity__c ); Novarun parses the class file using predefined tokens, converts into the XML and then create facts(facts are like data structures) from the xml file using factengine. While creating the fact for this file, it tries to check if the pagereference contains hard coded values ; In Normal cases it contains a VFPage URL so it changes it into a apex statement, But here its rather a SOQL query; so when it tries to type cast a ApexDatabaseQuery Statement into an Apex Statement, it throws the ClassCast Exception. | The solution is to check the feasibility of converting into a databasequerystatement which involves altering the entire fact engine/Tokens as well |  |  | Dhivya |  | 22/07/2015 | 22/07/2015
2 | Code Metrics | Few Failures in storing the trigger files in Novarun | Few Novarun files fails with the below exception “Specified External ID for Name in entity AIES_ACCENTURE__Files__c value length is 81 which exceeds maximum field length of 80” because the Name column in the file object has the size of 80 only. | Closed | Medium | Few trigger file names are not stored in the novarun object because the name field of the object can accommodate only up to 80 characters. | The solution is to restrict the file names up to 80 characters. |  |  | Dhivya |  | 14/7/2015 | 14/7/2015
3 | Layouts metadata | Few layouts are not inserted | Few layouts are not inserted into ASD | Closed | Medium | Some layouts are not getting inserted into salesforce because they don’t have the corresponding objects inserted which acts as a foreign key. The metadata api will not retrieve and insert the objects that belong to the managed package and so the layouts of those objects also will not be inserted. | Not a Bug |  |  | Dhivya |  | 2015-08-07 | 2015-08-07
4 | Validation Rules | validation Rules of managed package are also analysed: | validation Rules of managed package are also analysed: | Closed | Medium | The salesforce metadata api is designed in such a way that except objects, all other components belonging to the managed package are also retrieved. | Not a Bug |  |  | Dhivya |  | 2015-08-07 | 2015-08-07
5 | Approval Processes | Few approval processes are not inserted | Few approval processes are not inserted into ASD | Closed | Medium | Some approval processes are not getting inserted into salesforce because they don’t have the corresponding objects inserted which acts as a foreign key. The metadata api will not retrieve and insert the objects that belong to the managed package and so the approval processes of those objects also will not be inserted. | Not a Bug |  |  | Dhivya |  | 2015-08-07 | 2015-08-07
6 | Approval Processes | Four approval processes failed to insert | Four approval processes failed to insert | Open | Medium | Meanwhile, the below approval processes have the same label name and while inserting the primary key(combination of portfolioname+objectname+labelname), it gives the “DUPLICATE_VALUE” error. ge_pw_order__ccustom ro e series order ¦¦ ge_pw_order__ccustom ro e series order v2 GE_PW_Gas_ITO¦¦GE_PW_Gas_ITO_New GE_PW_Gas_Product_Supply¦¦GE_PW_Gas_Product_Supply_New | The code need to be altered to set the combination of portfolioname+objectname+filename or any other unique name as the external id instead of label name. Needs review. This is Client specific |  |  | Dhivya
7 | Query Locator | Metadata xmls are not retrieved due to invalid query locator errors | Metadata xmls are not retrieved due to invalid query locator errors | Closed | Medium | The error is due to the salesforce querylocator limit wherein Each Salesforce user can have up to 10 query cursors open at a time. This is a hard coded limit that cannot be increased. If 10 query locator cursors are opened when a client application attempts to open a new one, then the oldest cursor is released. If a call is attempted to an expired or released cursor, salesforce will return the INVALID_QUERY_LOCATOR error | Split Assignment Rule to two Package.xml then Rerun Extraction Tool |  |  | Dhivya |  | 26/6/2015 | 26/6/2015
8 | Objects | Missing below objects in PowerMap: MacroAction Site FeedItem StreamingChannel TC_Included_Profiles__c MacroInstruction GE_HQ_Integration_Activity__c | Few Objects are missing in the Object Power Map | In Progress | Medium | TC_Included_Profiles__c - Custom setting MacroInstruction - No fields in the object Site - No fields in the object MacroAction - No fields in the object StreamingChannel - No fields in the object When there are no fileds, the objects will not be inserted into the powermap Case object - visible but some of the metadata not displaying count- to be addressed | In Progress |  |  | Aravindan